## Master Timeline
HOOP IQ — Master Project Timeline
CECS490A/B • Team 2 • California State University, Long Beach • Fall 2025 – Spring 2026
# | Week | Dates | Phase / Milestone | Tasks & Accomplishments | Status | Notes / Deviations
STATUS KEY: ✅ On Schedule ⚠️ Minor Delay / Adjusted ❌ Delayed 🔵 In Progress / Upcoming ✳️ Milestone / Demo
SEMESTER 1 — CECS490A ¦ Fall 2025 (Aug 25 – Dec 12, 2025)
1 | Week 1 | Aug 25 – Aug 29 | Kickoff & Planning | Project selection finalized. Team roles assigned (PM: Margulies, Hardware: Mejia/Orozco, CV: Kelly, Web: Hong). Initial project scope defined. Began system architecture research. | ✅ On Schedule | —
2 | Week 2 | Sep 1 – Sep 5 | Research & Architecture | Researched IR break-beam sensors, piezo vibration detection, Raspberry Pi 5 capabilities, and OpenCV for basketball tracking. Began drafting system block diagram. | ✅ On Schedule | —
3 | Week 3 | Sep 8 – Sep 12 | Research & Architecture | Completed system architecture definition. Subsystem responsibilities finalized. Selected ESP32 as sensor controller. Confirmed Rust for Raspberry Pi software stack. | ✅ On Schedule | —
4 | Week 4 | Sep 15 – Sep 19 | Research & Architecture | Completed block diagram and subsystem interface definitions. Drafted component list and initial BOM. Finalized data flow: ESP32 → Pi → Tailscale → Flask → hoopiq.shop. | ✅ On Schedule | —
5 | Week 5 | Sep 22 – Sep 26 | Design & Procurement | Subsystem designs finalized. Hardware orders submitted through university procurement (ESP32, IR sensors, piezo discs, ADC, resistors, wiring). Pi environment setup began. | ✅ On Schedule | —
6 | Week 6 | Sep 29 – Oct 3 | Design & Procurement | Component orders placed. Raspberry Pi 5 received and initial OS setup completed. Rust toolchain and Cargo build environment configured. Placeholder camera testing started. | ✅ On Schedule | —
7 | Week 7 | Oct 6 – Oct 10 | Hardware Procurement — DELAYED | University procurement orders delayed. Critical sensors (IR, piezo, ESP32) not yet received. Team members began purchasing components out-of-pocket to prevent timeline slip. | ❌ Delayed | University procurement significantly slower than anticipated. Out-of-pocket purchases made by team.
8 | Week 8 | Oct 13 – Oct 17 | Software Prep (hardware delayed) | Shifted focus to software while awaiting parts. Designed serial packet format (EVENT_TYPE,TIMESTAMP,IR_FLAG,PIEZO_FLAG). Researched MOG2 background subtraction. Drafted ESP32 firmware state machine architecture. | ⚠️ Adjusted | Pivot to software-first development to use downtime productively.
9 | Week 9 | Oct 20 – Oct 24 | Software Prep (hardware delayed) | OpenCV integration tested on Pi using placeholder video. Rust Arc/Mutex shared state model designed. ESP32 firmware ISR and threshold logic written and reviewed off-device. | ⚠️ Adjusted | —
10 | Week 10 | Oct 27 – Oct 31 | Software Prep / Hardware Arriving | Remaining out-of-pocket hardware components arrived. Began breadboard prototyping of ESP32 + IR sensor pair. Verified 3.3V IR emitter operation. Initial piezo readings captured. | ⚠️ Adjusted | Recovery from procurement delay begins.
11 | Week 11 | Nov 3 – Nov 7 | Hardware Prototyping | ESP32 firmware compiled and flashed. IR beam break detection confirmed. Piezo threshold calibration begun. GPIO pin mapping finalized (GPIO 27: IR, GPIO 32/35: piezo backboard, GPIO 34: piezo rim). | ✅ On Schedule | —
12 | Week 12 | Nov 10 – Nov 14 | Hardware Prototyping | Shot event state machine implemented: MAKE, SWISH, RIM_CONTACT, MISS classification. Dynamic baseline filtering added to piezo firmware. Serial packet transmission to Pi tested with synthetic events. | ✅ On Schedule | —
13 | Week 13 | Nov 17 – Nov 21 | Integration Planning & Prototype | Mini-hoop prototype assembled. IR beam physically mounted across rim plane. Piezos mounted to backboard and rim. Wired serial confirmed from ESP32 to Pi. Rust serial parser implemented on Pi side. | ✅ On Schedule | —
14 | Week 14 | Nov 24 – Nov 28 | Prototype Refinement | Thanksgiving week. Threshold tuning continued. Camera mounted and initial ball detection tested using MOG2. Dual-stream FFmpeg/v4l2loopback architecture prototyped. Tailscale account configured. | ✅ On Schedule | Thanksgiving — reduced availability but continued progress.
15 | Week 15 | Dec 1 – Dec 5 | Proof-of-Concept Demo Prep | Full end-to-end proof-of-concept assembled. ESP32 detecting shots and transmitting to Pi. Pi parsing serial events. Flask backend skeleton deployed on Render. Dashboard prototype running at hoopiq.shop. | ✅ On Schedule | —
16 | Week 16 | Dec 8 – Dec 12 | ✳️ Semester 1 Final Demo / Wrap-Up | Proof-of-concept demonstration completed. All subsystems functional at baseline level: sensor detection, serial comm, Pi processing, cloud backend, and dashboard. Semester 1 concluded. Report submitted. | ✅ On Schedule | Proof-of-concept successfully demonstrated. Strong foundation heading into 490B.
SEMESTER 2 — CECS490B ¦ Spring 2026 (Jan 21 – May 9, 2026)
17 | Week 1 | Jan 21 – Jan 25 | Semester 2 Kickoff | Semester 2 kickoff. Hardware team began refining hoop sensor mounting configuration. Reviewed Semester 1 lessons learned. Updated project plan and set Demo 1 target for Week 4. | ✅ On Schedule | —
18 | Week 2 | Jan 26 – Jan 31 | Hardware Refinement | IR beam alignment adjusted for more reliable shot detection. Piezo sensor mounting positions iterated — tested left, center, and right backboard placement for optimal vibration response. Wiring stabilized with cable management. | ✅ On Schedule | —
19 | Week 3 | Feb 2 – Feb 6 | Hardware Refinement & Demo 1 Prep | Finalized sensor mounting configuration on backboard. Full hardware assembly stabilized with mechanical fasteners. Sensor alignment re-verified post-mounting. Demo 1 test runs performed: 100% make detection, 100% rim contact. | ✅ On Schedule | —
20 | Week 4 | Feb 9 – Feb 13 | ✳️ Demo 1 — Hoop Sensor Subsystem | Demo 1 completed. ESP32-based shot detection demonstrated. IR + piezo dual-sensor event classification confirmed operational. Make detection: 3/3 (100%). Rim contact: 2/2 (100%). Serial comm to Pi stable. | ✅ On Schedule | Demo 1: PASS. All targets met or exceeded.
21 | Week 5 | Feb 16 – Feb 20 | CV Pipeline & Integration | Computer vision pipeline development accelerated. MOG2 background subtraction refined. Ball contour filtering tuned (area + aspect ratio constraints). Rolling position buffer implemented for trajectory smoothing. | ✅ On Schedule | —
22 | Week 6 | Feb 23 – Feb 27 | CV Pipeline & Zone Classification | Shot zone classification implemented: Left Corner 3, Right Corner 3, Above Break 3, Paint, Mid-Range. Arc height calculation (peak Y relative to release point) and entry angle estimation implemented. AHEAD of planned milestone. | ✅ On Schedule | Shot zone classification and arc/angle features completed ahead of schedule.
23 | Week 7 | Mar 2 – Mar 6 | CV + Backend + Stretch Goals | Heatmap visualization implemented in dashboard. Airball classification logic added on Pi side (5-second timeout from detected shot attempt). CSV session export added to dashboard. All three stretch goals completed. | ✅ On Schedule | Stretch goals (zone, heatmap, export) all completed by Week 7 — well ahead of plan.
24 | Week 8 | Mar 9 – Mar 13 | Full Pipeline Integration | End-to-end data pipeline validated: ESP32 event → serial → Pi Rust binary → Tailscale tunnel → Render Flask API → hoopiq.shop dashboard. Latency confirmed under 1 second. Dual-stream RTSP confirmed stable. | ✅ On Schedule | —
25 | Week 9 | Mar 16 – Mar 20 | CV Demo Prep | Demo 2 preparation. Ball detection validated under varied lighting. Trajectory overlay confirmed rendering on dashboard. WebRTC/WHEP stream confirmed accessible from external browser. System stability tested over extended session. | ✅ On Schedule | —
26 | Week 10 | Mar 23 – Mar 27 | ✳️ Demo 2 — Computer Vision Subsystem | Demo 2 completed. Live ball detection and dual-stream camera architecture demonstrated. Logitech C922x → Rust+OpenCV processing stream + RTSP broadcast both operational. Ball trajectory overlay confirmed live on dashboard. | ✅ On Schedule | Demo 2: PASS. CV subsystem met all planned targets.
27 | Week 11 | Mar 30 – Apr 3 | Backend & Dashboard Integration | Flask backend on Render validated with full session data flow. Dashboard displaying shot log, statistics, shot type breakdown, shooting percentage, heatmap, and zone percentages. Real-time API polling confirmed. | ✅ On Schedule | —
28 | Week 12 | Apr 6 – Apr 10 | Backend & Dashboard Integration | Session management, counter reset, and export functionality validated end-to-end. Dashboard UI polished. API endpoint error handling added. Render deployment confirmed stable under continuous use. | ✅ On Schedule | —
29 | Week 13 | Apr 13 – Apr 17 | ✳️ Demo 3 — Web/App Subsystem | Demo 3 completed. Backend + dashboard integration demonstrated with mock and live data. Shot log, stats, heatmap, and CSV export all confirmed functional. Real-time data flow from Render to hoopiq.shop confirmed. | ✅ On Schedule | Demo 3: PASS. All dashboard targets met.
30 | Week 14 | Apr 20 – Apr 24 | Full System Integration & Cleanup | All subsystems integrated simultaneously in real-world shooting conditions. Latency measured end-to-end (sensor event to dashboard update). System stability tested over 30+ minutes of continuous operation. Dashboard UI final polish begun. | ✅ On Schedule | —
31 | Week 15 | Apr 27 – May 1 | Final Integration, Polish & Demo 4 Prep | Final three weeks of integration and cleanup completed. Dashboard fully polished and stabilized for expo. Hoop sensor, Pi, Tailscale tunnel, Flask backend, and hoopiq.shop all confirmed running simultaneously. Demo 4 dry runs completed. | ✅ On Schedule | Final system state confirmed ready for Demo 4 and Expo.
32 | Week 16 | May 4 – May 4 | ✳️ Demo 4 — Final Integrated Demo (5/4/26) | Final integrated system demonstration. Full end-to-end real-time operation: hoop sensing + CV pipeline + live dashboard. [INSERT: shot count, make accuracy, and latency measured at demo] | 🔵 | Demo 4 scheduled 5/4/26.
33 | Week 17 | May 5 – May 9 | ✳️ Senior Project Expo (5/7/26) | Hoop IQ presented at CSULB Senior Project Expo. Full working system demonstrated live: hoop assembly, Raspberry Pi, camera, and dashboard accessible from any browser. [INSERT: expo observations and outcomes] | 🔵 | Expo: 5/7/26.
PROJECT SUMMARY
| Total Weeks Tracked |  |  | 33 weeks (16 × Semester 1 + 17 × Semester 2)
| On Schedule |  |  | 27 weeks
| Adjusted / Minor Delay |  |  | 3 weeks (Oct 6–24, Sem 1 Wks 7–9 — procurement pivot)
| Delayed |  |  | 1 week (Oct 6–10, Sem 1 Wk 7 — university procurement)
| In Progress / Upcoming |  |  | 2 weeks (Demo 4: 5/4/26 • Expo: 5/7/26)
| Subsystem Demos |  |  | Demo 1 ✅ (Feb 2026) • Demo 2 ✅ (Mar 2026) • Demo 3 ✅ (Apr 2026) • Demo 4 🔵 (May 4, 2026)
| Senior Project Expo |  |  | May 7, 2026 — CSULB
| Stretch Goals |  |  | Shot Zone Classification ✅ ¦ Heatmap ✅ ¦ CSV Export ✅ (all completed Wks 6–7, ahead of schedule)